## Basic Gantt Chart
HCI GANTT CHART
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER(S) LEADING TASK | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
1 | Topic definition and understanding of the problem | 2019-09-18 | 2019-09-23 | 0 | 6 | All team | 100%
2 | Team Meeting - Discussion | 2019-09-30 | 2019-09-30 | 12 | 1 | All team | 100%
3 | Team Meeting - Design Aleternatives | 2019-10-07 | 2019-10-07 | 19 | 1 | All team | 100%
4 | Balsamiq Prototype - 4 wireframe pages total | 2019-10-07 | 2019-10-16 | 19 | 10 | Brendan/Nick | 100%
5 | Design Alternatives Powerpoint | 2019-10-07 | 2019-10-16 | 19 | 10 | Adam | 100%
6 | Team Meeting - Before Presentation | 2019-10-13 | 2019-10-13 | 25 | 1 | All team | 100%
7 | Team Presents Powerpoint | 2019-10-14 | 2019-10-14 | 26 | 1 | All team | 100%
8 | Evaluate Presentation Feedback | 2019-10-14 | 2019-10-19 | 26 | 6 | All team | 100%
9 | Decide where to develope website | 2019-10-20 | 2019-11-11 | 32 | 23 | All team | 100%
10 | Evaluation Plan | 2019-10-28 | 2019-11-12 | 40 | 16 | Nick, Adam, Brendan | 100%
11 | Heuristic Evaluation Method | 2019-11-11 | 2019-11-20 | 54 | 10 | All team | 100%
12 | Card Sorting Evaluation Method | 2019-11-11 | 2019-11-20 | 54 | 10 | All team | 100%
13 | Survey Evaluation Method | 2019-11-11 | 2019-11-20 | 54 | 10 | All team | 100%
14 | Prototype - Homepage | 2019-11-11 | 2019-11-30 | 54 | 20 | Lauren, Adam, Nick | 100%
15 | Prototype - Search/Map Page | 2019-11-11 | 2019-11-30 | 54 | 20 | Lauren, Adam, Nick | 100%
16 | Prototype - Log in/Account menu | 2019-11-11 | 2019-11-30 | 54 | 20 | Lauren, Adam, Nick | 100%
17 | Edit Prototype Based on User Testing | 2019-11-11 | 2019-12-11 | 54 | 31 | Lauren | 85%
18 | Final Presentation | 2019-12-01 | 2019-12-11 | 74 | 11 | All team | 0%
19 | Final Report | 2019-12-01 | 2019-12-11 | 74 | 11 | All team | 0%
20 |  | 2019-11-11 | 2019-11-11 | 54 | 1 |  | 0%
21 |  | 2019-11-11 | 2019-11-11 | 54 | 1 |  | 0%
22 |  | 2019-11-11 | 2019-11-11 | 54 | 1 |  | 0%
23 |  | 2019-11-11 | 2019-11-11 | 54 | 1 |  | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Manual Chart
ID | TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
1 | Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 2 | Nathan
2 |  |  |  | 0 | Meredith | bar: WEEK 2 M to WEEK 2 T
3 | Review Landing Page Design | 2018-01-11 | 2018-01-16 | 4 | Brandon | bar: WEEK 1 F to WEEK 2 Th
4 | Build Landing Page | 2018-01-14 | 2018-01-19 | 5 | Michael | bar: WEEK 2 T to WEEK 3 M
5 | Code Review Landing Page | 2018-01-17 | 2018-01-21 | 3 | Rachel | bar: WEEK 2 Th to WEEK 3 W
6 | Promote Landing Page | 2018-01-20 | 2018-01-23 | 2 | Annie | bar: WEEK 3 T to WEEK 3 Th
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])